AI SKINCARE INTELLIGENCE SYSTEM – PRODUCT BACKLOG V5

COMPREHENSIVE AGILE PRODUCT BACKLOG FOR MVP & PHASE 2

Status: Ready for Sprint Planning
Version: 5.0
Created: November 30, 2025
Last Updated: November 30, 2025
Document Owner: Product Manager
Classification: Internal – Business Sensitive

EXECUTIVE SUMMARY

This comprehensive product backlog contains 650+ mapped user stories across 19 integrated EPICs, derived directly from the AI Skincare Intelligence System SRS V5 (Enhanced). The backlog is organized for immediate development sprint planning and represents a complete 16-week MVP development plan (8 sprints × 2 weeks each) with Phase 2 roadmap (12 weeks post-launch) for advanced features.

KEY BUSINESS METRICS

| Metric | Value | Notes |
| --- | --- | --- |
| Total User Stories | 650+ | Mapped from SRS requirements |
| Total Epics | 19 | Cross-functional feature groupings |
| Total Backlog Items | 2,000+ | Including sub-tasks and acceptance criteria |
| MVP Stories | 60 | Prioritized for Release 1.0 |
| Phase 2 Stories | 13 | Post-launch advanced features |
| Estimated Story Points (MVP) | 350–400 | Baseline velocity 40–50 per sprint |
| MVP Development Timeline | 16 weeks | 8 two-week sprints |
| Recommended Team Size | 12–14 engineers | 4–5 backend, 3–4 frontend, 2–3 ML, 2–3 QA/DevOps |
| Cross-Platform Coverage | Web, iOS, Android | All platforms MVP-ready by end of Sprint 8 |
| ML Fairness Target | ±5% accuracy across Fitzpatrick I–VI | Baseline monitoring from Sprint 1 |

SUCCESS CRITERIA FOR MVP RELEASE

| Category | Target | Verification | Owner |
| --- | --- | --- | --- |
| Feature Coverage | 100% of 60 MVP stories shipped | Sprint board completion | Product Team |
| Performance | API latency p95 < 500ms | APM monitoring (Datadog/New Relic) | Backend Lead |
| App Performance | App launch < 2 seconds | Lighthouse, WebPageTest | Frontend Lead |
| ML Fairness | ±5% accuracy (Fitzpatrick I–VI) | Validation datasets + fairness audit | ML Lead |
| Accessibility | WCAG 2.1 AA 100% compliance | Third-party audit report | QA Lead |
| Reliability | Critical bugs < 1% | Production error rate monitoring | QA Lead |
| User Retention | Day 30 > 40% cohort retention | Analytics dashboard | Product Lead |
| User Satisfaction | App store rating ≥ 4.5 stars | Public app store reviews | Product Lead |

TABLE OF CONTENTS

- EPIC 1: User Accounts & Onboarding

- EPIC 2: Face Scan & AI Analysis

- EPIC 3: Digital Twin Engine

- EPIC 4: Skin Mood Index

- EPIC 5: Product Intelligence Engine

- EPIC 6: Routine Builder Engine

- EPIC 7: Progress Tracking Engine

- EPIC 8: Environmental Intelligence

- EPIC 9: Predictive Forecasting

- EPIC 10: Scenarios Engine

- EPIC 11: Counterfeit Detection

- EPIC 12: Dermatology Risk Radar

- EPIC 13: N-of-1 Experiments

- EPIC 14: External Integrations

- EPIC 15: Tele-Dermatology

- EPIC 16: ML Engineering & Model Development

- EPIC 17: Infrastructure & DevOps

- EPIC 18: UX/Design System

- EPIC 19: Non-Functional Requirements & QA

- Sprint Planning Roadmap

- Risk Register & Mitigation

- Resource Allocation

- Phase 2 Release Plan

EPIC 1: USER ACCOUNTS & ONBOARDING

SRS Traceability: UR1, UR13, FR44–FR46, NFR4, NFR6
Priority: CRITICAL (Sprint 1)
Total Stories: 42
Estimated Story Points: 85–100
Team Assignment: Backend Lead + 2 Backend Engineers
Completion Target: End of Sprint 2

EPIC OBJECTIVE

Establish secure, scalable user account infrastructure with email-based authentication, multi-device session management, robust onboarding flows, and baseline profile capture to enable personalized Digital Twin™ creation for each user.

EPIC SUCCESS METRICS

| Metric | Target | Measurement | Owner |
| --- | --- | --- | --- |
| User registration success rate | ≥ 95% | % of attempted registrations completed | Backend Lead |
| Account activation (email verified) | ≥ 85% | % of registered users who verify email within 7 days | Product Lead |
| Onboarding completion rate | ≥ 80% | % of new users completing full onboarding flow | Product Lead |
| Login success rate | ≥ 98% | % of authentication attempts by verified users | Backend Lead |
| Session stability | ≥ 99.5% | % of active sessions maintained without dropout | Backend Lead |
| Multi-device session handoff | ≥ 97% | % of users successfully switching devices and maintaining session | Frontend Lead |
| Password reset success | ≥ 90% | % of password recovery requests completed | Backend Lead |
| Account security score | 100% | Zero confirmed account takeovers or unauthorized access incidents | Security Lead |

USER STORY 1.1.1: EMAIL REGISTRATION

Priority: CRITICAL | Story Points: 8 | Sprint: 1
Complexity: Medium | Estimated Hours: 20–25 | Assigned To: Backend Engineer #1

USER STORY STATEMENT

As a new user, I want to create an account using email + password, so that I can access all personalized skincare features and maintain my Digital Twin™ over time.

ACCEPTANCE CRITERIA (12)

- Email format validation follows RFC 5322 standard with MX record verification on submit

- Duplicate emails rejected immediately with clear 409 Conflict error message

- Password complexity enforced real-time: minimum 8 characters, 1 UPPERCASE, 1 number, 1 special character (@#$%^&*)

- Passwords hashed using Argon2id (cost parameter ≥ 12, time_cost ≥ 2, memory_cost ≥ 65536) or bcrypt equivalent

- User creation timestamp recorded in UTC (immutable, never modified after account creation)

- Verification email sent within 2 seconds post-registration, with retry queue for failures

- Resend verification link allowed maximum 3 times per hour (rate-limited by source IP address + user session)

- Verification token cryptographically random (≥ 32 bytes), unique, and expires after 24 hours (enforced via TTL index)

- Full OWASP Top 10 compliance (A1 Injection, A2 Broken Auth, A3 XSS, A4 XXE, A5 Broken Access Control, A6 Security Misconfiguration, A7 XSS, A8 Insecure Deserialization, A9 Log Injection, A10 Insufficient Logging)

- All registration events logged asynchronously (timestamps, IP address, email domain, user consent status) to immutable audit log with no PII stored in logs by default

- Backend response latency p95 < 1.5 seconds (measured over 1000+ concurrent registration requests via K6 load test, including email send SLA)

- Email verification mandatory before first login; unverified accounts cannot access app (403 Forbidden error returned)

TECHNICAL REQUIREMENTS

Endpoint Specification:
POST /auth/register
Content-Type: application/json
Rate Limit: 10 requests/minute per IP address

REQUEST PAYLOAD:
{
"email": "user@example.com",
"password": "SecurePass123!"
}

RESPONSE (201 Created):
{
"user_id": "uuid",
"email": "user@example.com",
"verification_status": "pending",
"created_at": "2025-11-30T21:15:00Z",
"message": "Verification email sent. Please check your inbox."
}

RESPONSE (409 Conflict - Duplicate):
{
"error": "Email already registered",
"code": "DUPLICATE_EMAIL"
}

RESPONSE (400 Bad Request - Validation):
{
"error": "Password does not meet complexity requirements",
"code": "WEAK_PASSWORD"
}

Security & Performance:

- Rate limiting: 10 registrations/minute per IP (enforced via API gateway or Redis)

- Database transaction isolation: READ_COMMITTED minimum to prevent race conditions on email uniqueness

- Response time SLA: p95 latency < 1.5 seconds (includes email send delay)

- Connection pool: minimum 20 database connections, maximum 100

DATABASE SCHEMA

TABLE: users

- user_id (UUID PRIMARY KEY)

- email (VARCHAR(255) UNIQUE NOT NULL)

- password_hash (VARCHAR(255) NOT NULL, Argon2 format)

- created_at (TIMESTAMP UTC NOT NULL DEFAULT CURRENT_TIMESTAMP)

- verified_at (TIMESTAMP UTC, NULL until email verified)

- last_login_at (TIMESTAMP UTC, NULL)

- account_status (ENUM: active, suspended, deleted)

- metadata (JSONB: preferences, consent_flags)

TABLE: verification_tokens

- token_id (UUID PRIMARY KEY)

- user_id (UUID NOT NULL REFERENCES users(user_id) ON DELETE CASCADE)

- token_hash (VARCHAR(255) UNIQUE NOT NULL)

- expires_at (TIMESTAMP UTC NOT NULL)

- used_at (TIMESTAMP UTC, NULL until consumed)

- created_at (TIMESTAMP UTC NOT NULL)

INDEXES:

- idx_users_email ON users(email)

- idx_users_verified_at ON users(verified_at)

- idx_verification_tokens_user_id ON verification_tokens(user_id)

- idx_verification_tokens_expires_at ON verification_tokens(expires_at)

QA TEST MATRIX

| Test Case ID | Scenario | Input | Expected Result | Pass/Fail |
| --- | --- | --- | --- | --- |
| REG-001 | Valid registration | email: user@example.com, password: SecurePass123! | 201 Created, email sent, token generated | ☐ |
| REG-002 | Duplicate email | email: user@example.com (exists) | 409 Conflict error | ☐ |
| REG-003 | Weak password | password: Pass1 (7 chars) | 400 Bad Request | ☐ |
| REG-004 | Missing special char | password: Password123 | 400 Bad Request | ☐ |
| REG-005 | Rate limit exceeded | 15 requests in 60 seconds from same IP | 429 Too Many Requests | ☐ |
| REG-006 | Invalid email format | email: notanemail | 400 Bad Request | ☐ |
| REG-007 | Expired token | Click verification link after 25 hours | 401 Unauthorized | ☐ |
| REG-008 | SQL injection | email: admin'; DROP TABLE users;-- | Sanitized, no error, registration fails safely | ☐ |
| REG-009 | XSS attempt in email | email: @test.com | Sanitized, treated as literal email | ☐ |
| REG-010 | Unicode password | password: Ëmôji🔒Pass123 | 201 Created | ☐ |
| REG-011 | Concurrent registrations | 100 simultaneous requests same email | Only 1 succeeds, 99 get 409 | ☐ |
| REG-012 | Email service failure | SendGrid API unavailable | 500 error, user registration rolled back or queued | ☐ |

PERFORMANCE TARGETS & LOAD TESTS

| Metric | Target | Tool | Baseline |
| --- | --- | --- | --- |
| Registration latency (p95) | < 1.5 seconds | Datadog APM | TBD |
| Email delivery time | < 2 seconds | SendGrid webhook logs | TBD |
| Database query (email check) | < 100ms | Query analyzer | TBD |
| Token generation | < 50ms | APM | TBD |
| Sustained load | 1000 registrations/minute | K6 load test | TBD |
| Connection pool utilization | < 80% at peak | Database monitoring | TBD |

SECURITY CHECKLIST

- ☐ OWASP Top 10 compliance verified (A1-A10)

- ☐ No hardcoded secrets, API keys in code

- ☐ Input validation on all form fields (client + server)

- ☐ Passwords never logged or exposed in error messages

- ☐ Rate limiting enforced at API gateway

- ☐ HTTPS/TLS 1.3 required for all endpoints

- ☐ CORS policies restrict to known front-end domains

- ☐ Email verification token is cryptographically random (≥ 32 bytes)

- ☐ Argon2 parameters reviewed (time_cost, memory_cost, parallelism)

- ☐ Database connection uses SSL/TLS

- ☐ Audit logs immutable (append-only)

DEPENDENCIES

- None (foundational story, no prior dependencies)

DEFINITION OF DONE

- ☐ All 12 acceptance criteria verified via automated test matrix (100% coverage)

- ☐ Unit tests: ≥ 90% code coverage for registration business logic (Hashing, validation, rate limiting)

- ☐ Integration tests: full registration flow (email send → verification token → email click → account activate → login)

- ☐ Security audit completed and approved by Security Lead:

  - OWASP Top 10 (injection, XSS, CSRF, timing attacks, account enumeration)

  - Argon2 parameters validated by cryptography specialist

  - Rate limiting enforced at API gateway and database layer

  - Email service failover tested

- ☐ Load test (K6): 1,000 concurrent registrations/minute sustained ≥ 5 minutes, p99 latency < 2 seconds

- ☐ Database schema deployed to dev environment, migrated to staging with zero downtime migration strategy tested

- ☐ OpenAPI/Swagger documentation complete with request/response examples, error codes, rate limits

- ☐ Code reviewed by 2+ senior backend engineers with signed approval

- ☐ Performance baseline established (regression testing enabled for future sprints)

- ☐ WCAG 2.1 AA accessibility audit on registration form (labels, color contrast ≥ 4.5:1, keyboard nav, screen reader)

- ☐ Deployment to dev environment successful with canary rollout procedure documented

- ☐ Runbooks created for common troubleshooting scenarios (email service down, database connection issues, token generation failures)

- ☐ Documentation updated in wiki: API reference, architecture diagram, deployment guide

- ☐ Monitoring alerts configured: failed registrations > 5%, email delivery failures > 1%, latency p95 > 2 seconds

SUCCESS METRICS

| Metric | Target | Measurement | Threshold |
| --- | --- | --- | --- |
| Registration success rate | ≥ 95% | Monitoring dashboard (% successful registrations) | Alert if < 90% |
| Email delivery success | ≥ 99% | SendGrid bounce/delivery logs | Alert if < 98% |
| Mean registration latency | < 800ms | APM percentile metrics | Alert if p95 > 1.5s |
| Failed registration rate | < 3% | Error tracking (Sentry/Rollbar) | Alert if > 5% |
| Security vulnerabilities found | 0 | OWASP security scan | Fail if any critical/high |
| Duplicate email attempts | < 1% | Database audit logs | Monitor for spikes |

USER STORY 1.1.2: EMAIL LOGIN & MULTI-DEVICE SESSION MANAGEMENT

Priority: CRITICAL | Story Points: 8 | Sprint: 1
Complexity: Medium | Estimated Hours: 20–25 | Assigned To: Backend Engineer #2
Dependencies: Story 1.1.1 (Email Registration must be completed)

USER STORY STATEMENT

As a registered and email-verified user, I want to log in securely with my email + password and maintain active sessions across multiple devices (web, iOS, Android), so that I can access my personalized Digital Twin™, routines, progress, and product shelf seamlessly across all platforms while the system detects and prevents unauthorized access attempts.

ACCEPTANCE CRITERIA (12)

- Valid email/password combination logs user in successfully

- Invalid credentials return generic error without email enumeration

- Unverified email accounts redirected to email verification flow

- Login throttling enforced: 5 failed attempts → 5-minute cooldown per account

- JWT access token (15-minute lifetime) + refresh token (7-day lifetime) generated on successful login

- Refresh token rotation: each refresh generates new tokens, invalidates previous refresh token

- All login events logged (timestamp, IP, device_id, user_agent) for fraud detection

- Logout endpoint invalidates all tokens (access + refresh) and clears session

- Session persists across app restarts (mobile: encrypted local storage)

- Session expiration warning displayed 1 minute before token expiry

- Multi-device login supported with maximum 5 active sessions per user

- Login response latency < 1 second (p95)

TECHNICAL REQUIREMENTS

Endpoint Specifications:

POST /auth/login
Content-Type: application/json
Rate Limit: 5 failed attempts per account → 5-minute cooldown

REQUEST PAYLOAD:
{
"email": "user@example.com",
"password": "SecurePass123!",
"device_id": "optional-uuid",
"device_name": "optional-iPhone-12"
}

RESPONSE (200 OK):
{
"user_id": "uuid",
"email": "user@example.com",
"access_token": "eyJhbGc...",
"refresh_token": "eyJhbGc...",
"token_type": "Bearer",
"expires_in": 900,
"session_id": "uuid"
}

RESPONSE (401 Unauthorized - Invalid credentials):
{
"error": "Invalid email or password",
"code": "INVALID_CREDENTIALS"
}

RESPONSE (403 Forbidden - Account locked):
{
"error": "Too many failed login attempts. Please try again in 5 minutes.",
"code": "ACCOUNT_LOCKED",
"retry_after": 300
}

RESPONSE (403 Forbidden - Email not verified):
{
"error": "Please verify your email before logging in",
"code": "EMAIL_NOT_VERIFIED"
}

POST /auth/logout
Authorization: Bearer {access_token}

RESPONSE (200 OK):
{
"message": "Logged out successfully"
}

POST /auth/refresh
Content-Type: application/json

REQUEST PAYLOAD:
{
"refresh_token": "eyJhbGc..."
}

RESPONSE (200 OK):
{
"access_token": "eyJhbGc...",
"refresh_token": "eyJhbGc...",
"expires_in": 900
}

JWT Token Specification:

- Algorithm: RS256 (asymmetric) preferred, HS256 if single-server architecture

- Access token claims: user_id, email, iat, exp (15 minutes)

- Refresh token claims: user_id, session_id, iat, exp (7 days)

- Token stored in HTTP-only, secure cookies (web) or encrypted storage (mobile)

- Never expose token in URL, only in Authorization header

Session Management:

- Redis cache for active sessions (1-hour TTL)

- Session table schema: session_id, user_id, device_id, device_name, ip_address, user_agent, created_at, last_activity_at, expires_at

- Maximum 5 sessions per user; oldest session terminated when 6th device logs in

- Session update: last_activity_at refreshed on each API call (lazy refresh every 5 minutes)

Device Tracking for Fraud Detection:

- Log: device_id, user_agent, IP address, location (geo-IP if available)

- Alert on: impossible travel (same user logged in from different countries within impossible timeframe)

- Alert on: new device login (optional notification to user)

DATABASE SCHEMA

TABLE: sessions

- session_id (UUID PRIMARY KEY)

- user_id (UUID NOT NULL REFERENCES users(user_id))

- device_id (UUID)

- device_name (VARCHAR(100))

- ip_address (INET)

- user_agent (TEXT)

- created_at (TIMESTAMP UTC NOT NULL)

- last_activity_at (TIMESTAMP UTC NOT NULL)

- expires_at (TIMESTAMP UTC NOT NULL)

- is_active (BOOLEAN DEFAULT true)

TABLE: login_attempts

- attempt_id (UUID PRIMARY KEY)

- user_id (UUID REFERENCES users(user_id))

- ip_address (INET)

- success (BOOLEAN)

- timestamp (TIMESTAMP UTC NOT NULL)

- reason_if_failed (VARCHAR(100), e.g., 'invalid_password', 'account_locked')

TABLE: refresh_tokens

- token_id (UUID PRIMARY KEY)

- user_id (UUID NOT NULL REFERENCES users(user_id))

- session_id (UUID NOT NULL REFERENCES sessions(session_id))

- token_hash (VARCHAR(255) UNIQUE NOT NULL)

- expires_at (TIMESTAMP UTC NOT NULL)

- rotated_at (TIMESTAMP UTC)

- is_revoked (BOOLEAN DEFAULT false)

INDEXES:

- idx_sessions_user_id_active ON sessions(user_id, is_active)

- idx_sessions_expires_at ON sessions(expires_at)

- idx_login_attempts_user_id ON login_attempts(user_id)

- idx_login_attempts_timestamp ON login_attempts(timestamp)

- idx_refresh_tokens_user_id ON refresh_tokens(user_id)

QA TEST MATRIX

| Test Case ID | Scenario | Expected Result | Pass/Fail |
| --- | --- | --- | --- |
| LOGIN-001 | Valid email + password | 200 OK, tokens generated, session created | ☐ |
| LOGIN-002 | Invalid password | 401 Unauthorized, no tokens | ☐ |
| LOGIN-003 | Non-existent email | 401 Unauthorized (generic error) | ☐ |
| LOGIN-004 | Unverified email | 403 Email not verified, redirect to verification | ☐ |
| LOGIN-005 | 5 failed attempts | Account locked for 5 minutes | ☐ |
| LOGIN-006 | Logout | Tokens invalidated, session cleared | ☐ |
| LOGIN-007 | Multi-device login | 5 sessions allowed, 6th device terminates oldest | ☐ |
| LOGIN-008 | Token refresh | New access token + rotated refresh token issued | ☐ |
| LOGIN-009 | Expired access token | Automatic refresh if refresh token valid | ☐ |
| LOGIN-010 | Expired refresh token | 401 Unauthorized, redirect to login | ☐ |
| LOGIN-011 | Token tampering | Verification fails, 401 error | ☐ |
| LOGIN-012 | Session timeout (1 hour) | Auto-logout, redirect to login | ☐ |

PERFORMANCE TARGETS

| Metric | Target | Tool |
| --- | --- | --- |
| Login latency (p95) | < 1 second | Datadog APM |
| Session lookup | < 50ms | Database monitoring |
| Token generation/validation | < 100ms | APM |
| Refresh token operation | < 200ms | APM |

SECURITY CHECKLIST

- ☐ Timing-safe password comparison (bcrypt handles this automatically)

- ☐ Generic error messages prevent email enumeration attacks

- ☐ Account lockout enforced: 5 failures → 5-minute cooldown

- ☐ Session hijacking prevention: tie session to device_id + user_agent

- ☐ Refresh token rotation prevents token replay attacks

- ☐ HTTPS/TLS required for all login requests

- ☐ Cookies marked HTTP-only, Secure, SameSite=Strict

- ☐ CSRF token required for login form submissions

- ☐ All login events audited with IP + device info

DEPENDENCIES

- Depends on: Story 1.1.1 (Email Registration) – users must exist

DEFINITION OF DONE

- ☐ All 12 acceptance criteria verified

- ☐ Unit tests: ≥ 90% code coverage

- ☐ Integration tests: full login/logout/refresh flow on web, iOS, Android

- ☐ Security audit: timing attacks, token validation, session hijacking

- ☐ Load test: 500 concurrent logins/minute sustained

- ☐ Database migrations deployed to dev + staging

- ☐ OpenAPI documentation complete

- ☐ Code review by 2+ senior engineers

- ☐ Accessibility audit on login form (WCAG 2.1 AA)

- ☐ No performance regressions

SUCCESS METRICS

| Metric | Target | Measurement |
| --- | --- | --- |
| Login success rate | ≥ 98% | Dashboard % successful logins |
| Mean login latency | < 600ms | APM p95 latency |
| Refresh token success | ≥ 99.5% | Session refresh success % |
| Unauthorized hijackings | 0 | Security audit report |
| Fraud detection false positives | < 0.1% | Alert log review |

USER STORY 1.2: ONBOARDING FLOW & BASELINE PROFILE

Priority: CRITICAL | Story Points: 13 | Sprint: 1–2
Complexity: High | Estimated Hours: 30–40 | Assigned To: Frontend Lead + Backend Engineer #1

USER STORY STATEMENT

As a newly registered user, I want a guided onboarding experience where I set my skin goals, concerns, and take a baseline scan, so that the system can begin building my Digital Twin™ and personalized recommendations.

ACCEPTANCE CRITERIA (10)

- Onboarding screens guide user through: email verification → name/profile → skin goals → primary concerns → first scan

- Skin goals selected from preset options (clear acne, reduce redness, fade pigmentation, improve texture, boost hydration, general maintenance)

- Primary concerns selected with checkboxes (acne, sensitivity, redness, pigmentation, dryness, aging, texture)

- Guided first scan (step-by-step UI with real-time lighting feedback)

- Baseline Digital Twin profile generated and stored

- Onboarding completion tracked (timestamp, completion_status flag in users table)

- Post-onboarding, user can skip to dashboard or explore "Get Started" mini-tutorials

- Mobile and web onboarding flows have feature parity

- Accessibility: all form fields labeled, screen reader support, keyboard navigation

- Onboarding can be completed in < 5 minutes for average user

TECHNICAL REQUIREMENTS

Onboarding Flow Specification:

- Step 1: Email Verification (if not already completed) – resend verification link option

- Step 2: Profile Setup – name, age (optional), skin type (dry/oily/combination/sensitive)

- Step 3: Goals & Concerns – checkbox selection from presets

- Step 4: Baseline Scan – guided camera flow (see Story 2.1.1 for scan UI details)

- Step 5: Review & Confirm – show generated Digital Twin baseline, option to retake scan

- Step 6: Completion – celebrate with motivational message, link to dashboard

Database Updates:

- users table: add fields: onboarding_completed_at, skin_goals (JSONB), primary_concerns (JSONB), preferred_name (VARCHAR)

- Add onboarding_events table to track completion milestones

Frontend Components:

- Stepper component showing progress (1/6 → 2/6, etc.)

- Each step has forward/back navigation (except can only go back in review step)

- Option to skip to dashboard after baseline scan

SUCCESS CRITERIA

- ≥ 80% of new users complete onboarding

- Mean time to complete: < 5 minutes

- Baseline scans uploaded successfully: ≥ 95%

- User engagement day 1: ≥ 70% open app after onboarding

- NPS feedback on onboarding: ≥ 7/10

EPIC 1 ADDITIONAL STORIES (Summary)

- 1.3: Social Sign-Up (OAuth with Google/Apple) – 8 points, Sprint 2

- 1.4: Password Reset & Recovery – 5 points, Sprint 2

- 1.5: Two-Factor Authentication (2FA) – 8 points, Phase 2

- 1.6: Profile Management & Settings – 5 points, Sprint 1

- 1.7: Data Export (GDPR Compliance) – 8 points, Sprint 3

- 1.8: Account Deletion – 5 points, Sprint 3

- 1.9: Consent & Privacy Policy UI – 5 points, Sprint 1

- 1.10: Multi-Language Onboarding – 8 points, Phase 2

Epic 1 Total: 42 Stories, 85–100 Points

EPIC 2: FACE SCAN & AI ANALYSIS

SRS Traceability: UR2, FR6–FR9B, NFR1–NFR3, NFR12
Priority: CRITICAL (Sprint 2)
Total Stories: 53
Estimated Story Points: 150–180
Team Assignment: Frontend Lead + 1 Mobile Engineer + ML Lead

EPIC OBJECTIVE

Implement real-time guided face scanning with multi-platform camera support, real-time lighting feedback, face detection, and AI-powered skin analysis to generate comprehensive skin concern scores.

USER STORY 2.1.1: GUIDED SCAN UI WITH REAL-TIME FEEDBACK

Priority: CRITICAL | Story Points: 13 | Sprint: 2
Complexity: High | Estimated Hours: 30–35 | Assigned To: Frontend Lead + 1 Mobile Engineer

USER STORY STATEMENT

As a user wanting accurate skin analysis, I want real-time guidance while taking a face scan (proper positioning, lighting, angles), so that the system captures high-quality images for accurate AI analysis.

ACCEPTANCE CRITERIA (12)

- Face outline overlay visible in real-time, guides user to center and frame face correctly

- Lighting detection provides dynamic visual warnings (green = good, yellow = suboptimal, red = too dark/bright)

- Show micro-instructions on screen ("Center your face", "Look straight", "Move into light")

- Disable capture button if lighting quality is poor (dark or overly bright)

- Occlusion detection (hands, hair covering face, shadows) with visual guidance to remove

- Face angle detection enforces ≤ 15° deviation from straight-on position

- Portrait orientation only (portrait mode lock on mobile); show rotation prompt if landscape detected

- Web platform: include photo upload option as fallback (in case live camera unavailable)

- Warn if makeup, SPF, or gloss detected (may affect analysis accuracy)

- Single scan attempt must complete within 5 seconds (timeout enforced)

- All UI text includes ARIA labels for screen reader accessibility

- UX validated on low-end devices (≥ 3 years old: iPhone 8, Samsung Galaxy S10)

TECHNICAL STACK

WebRTC & Camera APIs:

- iOS: AVFoundation (native) or WebRTC for web

- Android: Camera2 API (native) or WebRTC for web

- Web: getUserMedia() API with WebRTC fallback

Real-Time ML Models:

- Face landmark detection: MediaPipe Face Mesh (468 landmarks) or TensorFlow.js equivalent

- Lighting quality scoring: Custom model using luminance histogram analysis

- Occlusion classifier: Hand detection (MediaPipe Hands) + hair segmentation (custom)

- Face angle calculator: Head pose estimation using landmarks (yaw, pitch, roll)

- Device orientation detection: Accelerometer (DeviceOrientation API)

Real-Time Rendering:

- Canvas API (web)

- Metal framework (iOS)

- Vulkan or OpenGL ES (Android)

Performance Requirements:

- Frame processing: < 33ms per frame (30 FPS minimum)

- Overlay rendering: < 16ms (60 FPS ideal)

- Memory usage: < 100MB on low-end devices

- Startup latency: < 2 seconds from screen load to live preview

ML MODEL REQUIREMENTS

The team must import or train the following models by Sprint 2:

| Model | Source | Training Data | Fairness Check |
| --- | --- | --- | --- |
| Face landmark detection | MediaPipe (pre-trained) | General face database | Test on Fitzpatrick I–VI |
| Lighting quality model | Custom training | Synthetic + real test images | Test across skin tones |
| Occlusion detection | Custom training | Hand + hair annotations | Test on diverse populations |
| Face angle classifier | Custom training | Rotated face images | Test on diverse face shapes |

DATABASE & STORAGE

New Tables:

- scan_jobs (scan_id, user_id, status, created_at, completed_at, raw_image_path, processed_image_path, lighting_score, angle_score, occlusion_flags, error_message)

- scan_quality_logs (scan_id, frame_count, avg_lighting_score, avg_angle_deviation, occlusion_count)

Cloud Storage:

- Raw images: encrypted S3/GCS bucket with automatic deletion after 90 days

- Processed images: same bucket with anonymized naming

UX REQUIREMENTS

Web/iOS/Android Consistency:

- Face frame overlay (dynamically sized based on distance from camera)

- Color-coded warning banners: green (good) → yellow (fix positioning) → red (stop, can't capture)

- Animated arrows pointing left/right/up/down to guide positioning

- Real-time numerical feedback: lighting score (0–100), angle deviation (degrees)

- Loading spinner + progress indicator during ML inference

- Text-to-speech announcements for guidance (optional, respects accessibility settings)

- Capture button enabled only when lighting + angle + no occlusion meet thresholds

Fallback Flows:

- Web: if camera unavailable, show photo upload button

- Mobile: if camera permission denied, show request permission screen + fallback to photo gallery

QA TEST COVERAGE

| Test Case | Description | Expected Result |
| --- | --- | --- |
| QA-SCAN-001 | Test with dark skin tones (Fitzpatrick V–VI) | Lighting detection works equally well |
| QA-SCAN-002 | Test with hats, glasses, scarves | Occlusion detection warns user |
| QA-SCAN-003 | Low-light environment (< 50 lux) | Lighting warning displayed, capture blocked |
| QA-SCAN-004 | High-light environment (> 1000 lux) | Lighting warning displayed, capture blocked |
| QA-SCAN-005 | iPhone 8 (6 years old) | No crashes, 30 FPS maintained |
| QA-SCAN-006 | Samsung Galaxy S10 (5 years old) | No crashes, acceptable performance |
| QA-SCAN-007 | With makeup applied | Makeup warning shown, but scan allowed |
| QA-SCAN-008 | With SPF/sunscreen visible | SPF gloss warning shown |
| QA-SCAN-009 | 45° angle (exceeds 15° threshold) | Positioning warning, capture blocked |
| QA-SCAN-010 | 5-second timeout | Auto-cancel if no capture attempted |
| QA-SCAN-011 | Screen reader enabled (NVDA/JAWS) | All labels announced |
| QA-SCAN-012 | Landscape orientation on mobile | Rotation prompt displayed |

PERFORMANCE TARGETS

| Metric | Target | Tool | Notes |
| --- | --- | --- | --- |
| Frame processing latency | < 33ms | APM (on-device profiling) | 30 FPS minimum |
| Overlay rendering latency | < 16ms | Frame rate monitoring | 60 FPS ideal |
| Memory usage (low-end device) | < 100MB | Memory profiler | Must not exceed system limits |
| Model startup latency | < 2 seconds | Profiler | Time from screen load to live preview |
| Lighting detection inference | < 100ms | On-device profiling | Per-frame latency |
| Occlusion detection inference | < 150ms | On-device profiling | Per-frame latency |

ACCESSIBILITY CHECKLIST

- ☐ All text on overlay has ARIA-label for screen readers

- ☐ Button labels descriptive (not just "Capture")

- ☐ Color contrast: warnings meet WCAG AA (4.5:1 for text)

- ☐ Keyboard navigation on web: Tab through all interactive elements

- ☐ Fonts: minimum 14px for guidance text (mobile)

- ☐ Text-to-speech announcements available but optional (users can disable)

DEPENDENCIES

- Depends on: Story 1.1.2 (Email Login) – user must be authenticated

- Depends on: ML pipeline setup (Story 16.1) – models must be trained/imported

DEFINITION OF DONE

- ☐ All 12 acceptance criteria verified on web, iOS, Android

- ☐ Face landmark, lighting, occlusion, and angle models working with ≥ 90% accuracy

- ☐ Fairness validation: models tested on Fitzpatrick I–VI (±5% variance max)

- ☐ Unit tests: ≥ 85% coverage for ML inference

- ☐ Integration tests: end-to-end scan capture on all 3 platforms

- ☐ Performance tested on low-end devices (no crashes, 30 FPS maintained)

- ☐ Cross-browser testing (Chrome, Firefox, Safari on web; native apps)

- ☐ Accessibility audit: WCAG 2.1 AA pass

- ☐ Scans saved to database with metadata (lighting_score, angle_score)

- ☐ Code review by ML + frontend leads

- ☐ User testing with 10+ participants (including diverse skin tones)

SUCCESS METRICS

| Metric | Target | Measurement |
| --- | --- | --- |
| Scan success on first attempt | ≥ 85% | % users complete scan without retries |
| Capture latency (p95) | < 2 seconds | APM measurement |
| Zero crashes on low-end devices | 100% | QA regression testing |
| User satisfaction | ≥ 4.2/5 stars | In-app survey post-scan |
| Fairness variance (Fitzpatrick I–VI) | ±5% | Validation dataset evaluation |

EPIC 2 ADDITIONAL STORIES (Summary)

- 2.2: AI Skin Concern Detection Engine – 13 points, Sprint 2

- 2.3: Skin Type Classification – 8 points, Sprint 2

- 2.4: Confidence Scoring & Uncertainty Handling – 5 points, Sprint 2

- 2.5: Fairness Monitoring Dashboard (ML Bias Tracking) – 8 points, Sprint 3

- 2.6: Regional Analysis (Forehead, Cheeks, Nose, Chin) – 13 points, Sprint 3

- 2.7: Scan Result Display & Score Breakdown – 8 points, Sprint 2

Epic 2 Total: 53 Stories, 150–180 Points

EPIC 3: DIGITAL TWIN ENGINE

SRS Traceability: FR1–FR1D, UR3
Priority: CRITICAL (Sprint 3–4)
Total Stories: 41
Estimated Story Points: 120–140
Team Assignment: Backend Lead + 1 Backend Engineer + ML Engineer

EPIC OBJECTIVE

Build and maintain a longitudinal, multi-dimensional model of each user's skin state, including global and regional profiles, timeline visualization, and scenario simulation capabilities.

Key Features:

- 9-dimensional skin state vector (texture, pores, redness, pigmentation, oil/hydration, sensitivity, barrier, microbiome)

- Regional sub-profiles for localized issues

- Time-stamped trajectory tracking

- Environment + product integration

- Scenario simulation (what-if analysis)

Epic 3 Total: 41 Stories, 120–140 Points

EPIC 4: SKIN MOOD INDEX

SRS Traceability: FR10–FR11, UR5
Priority: CRITICAL (Sprint 3)
Total Stories: 8
Estimated Story Points: 20–25

EPIC OBJECTIVE

Generate real-time Skin Mood classifications (balanced, inflamed, over-exfoliated, barrier-stressed, UV-overexposed, dehydrated) based on Digital Twin biomarkers and provide corresponding behavioral/product guidance.

Epic 4 Total: 8 Stories, 20–25 Points

EPIC 5: PRODUCT INTELLIGENCE ENGINE

SRS Traceability: FR23–FR27H, UR9, UR19–UR22
Priority: HIGH (Sprint 3–6)
Total Stories: 120
Estimated Story Points: 300–350

EPIC OBJECTIVE

Enable product scanning via barcode/OCR, ingredient safety profiling, product–skin suitability rating, and My Shelf inventory management with feedback learning.

Sub-Features:

- Ingredient Parser & OCR (17 stories) – Extract ingredients from packaging

- Safety Classification (20 stories) – Map ingredients to safety profiles

- Microbiome Disruption Index (10 stories) – Score microbiome impact

- Product–Skin Suitability Engine (30 stories) – Rate Safe/Caution/Not Recommended

- My Shelf Inventory (15 stories) – Maintain product library

- Cohort Insights (8 stories) – Aggregated user outcomes

Epic 5 Total: 120 Stories, 300–350 Points

EPIC 6: ROUTINE BUILDER ENGINE

SRS Traceability: FR18–FR19E, UR6, UR20
Priority: HIGH (Sprint 4–6)
Total Stories: 75
Estimated Story Points: 180–220

EPIC OBJECTIVE

Generate personalized AM/PM skincare routines using user's My Shelf inventory, tailored to skin state, environment, and forecast, with product interaction checking and Routine Safety Score.

Key Deliverables:

- AM routine generator (Cleanser → Treatment → Serum → Moisturizer → SPF)

- PM routine generator (barrier-focused)

- Product interaction checker

- Daily routine adapter (environment/mood-based)

- Habit gamification (badges, streaks)

- Burnout detection

Epic 6 Total: 75 Stories, 180–220 Points

EPIC 7: PROGRESS TRACKING ENGINE

SRS Traceability: FR35–FR36, UR4
Priority: HIGH (Sprint 5–6)
Total Stories: 40
Estimated Story Points: 100–120

EPIC OBJECTIVE

Display skin progress over 7/30/90-day timeframes with charts, before/after comparisons, improvement summaries, regression alerts, and correlation detection.

Epic 7 Total: 40 Stories, 100–120 Points

EPIC 8: ENVIRONMENTAL INTELLIGENCE

SRS Traceability: FR15–FR17, FR15A–FR15C, FR16A, UR7
Priority: HIGH (Sprint 5–7)
Total Stories: 30
Estimated Story Points: 70–85

EPIC OBJECTIVE

Integrate real-time environmental data (UV, temperature, humidity, pollution, wind) and provide environment-based recommendations, Skin Weather Score, travel mode detection, and climate profile learning.

Epic 8 Total: 30 Stories, 70–85 Points

EPIC 9: PREDICTIVE FORECASTING

SRS Traceability: FR12–FR14, FR12A–FR12B, UR8
Priority: PHASE 2 (Sprint 5–7)
Total Stories: 25
Estimated Story Points: 65–80

EPIC OBJECTIVE

Predict 7/30/90-day skin evolution based on historical scores, environment, routine adherence, and products, with uncertainty ranges and feedback recalibration.

Epic 9 Total: 25 Stories, 65–80 Points

EPIC 10: SCENARIOS ENGINE

SRS Traceability: FR49–FR50
Priority: PHASE 2 (Sprint 5–7)
Total Stories: 12
Estimated Story Points: 30–40

EPIC OBJECTIVE

Enable "what-if" scenario simulation (e.g., "remove fragrance", "add retinoid") with predicted outcomes and trade-off visualization.

Epic 10 Total: 12 Stories, 30–40 Points

EPIC 11: COUNTERFEIT DETECTION

SRS Traceability: FR28–FR29, FR28A, UR10
Priority: PHASE 2 (Sprint 5–8)
Total Stories: 10
Estimated Story Points: 25–30

EPIC OBJECTIVE

Detect packaging inconsistencies, label mismatches, and invalid barcodes to flag potential counterfeit products with risk scores.

Epic 11 Total: 10 Stories, 25–30 Points

EPIC 12: DERMATOLOGY RISK RADAR

SRS Traceability: FR32–FR34, UR12
Priority: PHASE 2 (Sprint 6–8)
Total Stories: 12
Estimated Story Points: 30–40

EPIC OBJECTIVE

Analyze multi-scan trends, identify concerning patterns, and suggest dermatology consultation with non-diagnostic language and provider directory.

Epic 12 Total: 12 Stories, 30–40 Points

EPIC 13: N-OF-1 EXPERIMENTS

SRS Traceability: FR54–FR57, BR14
Priority: PHASE 2 (Sprint 6–8)
Total Stories: 18
Estimated Story Points: 50–65

EPIC OBJECTIVE

Enable users to run personal skincare experiments (baseline → intervention → analysis) with automated tracking and evidence-based outcome summaries.

Key Features:

- System-suggested experiment templates

- Custom experiment creation

- Baseline period definition (2+ weeks)

- Intervention period execution (4–6 weeks)

- Automated adherence tracking

- Scan scheduling + user feedback collection

- Non-diagnostic outcome report generation

- Aggregate learning for similar user profiles

Epic 13 Total: 18 Stories, 50–65 Points

EPIC 14: EXTERNAL INTEGRATIONS

SRS Traceability: FR51–FR53
Priority: PHASE 2–3 (Sprint 7–8)
Total Stories: 8
Estimated Story Points: 20–25

EPIC OBJECTIVE

Provide secure APIs for partners to access product intelligence, export Digital Twin snapshots, and receive aggregated trend webhooks.

Epic 14 Total: 8 Stories, 20–25 Points

EPIC 15: TELE-DERMATOLOGY

SRS Traceability: FR58–FR60, BR15
Priority: PHASE 2–3 (Sprint 8+)
Total Stories: 6
Estimated Story Points: 18–24

EPIC OBJECTIVE

Integrate provider directory, optionally enable tele-dermatology consultations, and support clinician-friendly data sharing.

Epic 15 Total: 6 Stories, 18–24 Points

EPIC 16: ML ENGINEERING & MODEL DEVELOPMENT

SRS Traceability: FR9A, NFR1, NFR12–NFR13
Priority: CRITICAL (Sprint 1–8, parallel)
Total Stories: 80+
Estimated Story Points: 200–250

EPIC OBJECTIVE

Build, train, validate, deploy, and continuously monitor ML models for skin analysis, fairness across demographics, and real-time inference.

Sub-Features:

- Dataset Pipelines (15 stories) – Data annotation, stratified sampling, bias testing

- Model Training (20 stories) – CNN model development, hyperparameter tuning, fairness testing

- Model Serving (15 stories) – Inference API, edge deployment, batch prediction

- Model Monitoring (20 stories) – Drift detection, fairness monitoring, A/B testing

- Explainability (10 stories) – LIME/SHAP integration, user explanations

Epic 16 Total: 80+ Stories, 200–250 Points

EPIC 17: INFRASTRUCTURE & DEVOPS

SRS Traceability: NFR11, NFR15, NFR16, NFR17
Priority: CRITICAL (Sprint 1–8, parallel)
Total Stories: 20+
Estimated Story Points: 50–65

EPIC OBJECTIVE

Build scalable, secure backend infrastructure with CI/CD, multi-environment management, monitoring, backup/DR, and cross-platform deployment.

Features:

- CI/CD pipeline (auto-test, auto-deploy to dev/staging/prod)

- Infrastructure-as-code (Terraform/CloudFormation)

- Database migrations & versioning

- Logging & monitoring (ELK stack, Datadog, Sentry)

- Backup & disaster recovery (RTO < 4 hours, RPO < 1 hour)

- Kubernetes orchestration (if container-based)

- Load balancing & auto-scaling policies

- Security hardening (vulnerability scanning, penetration testing)

Epic 17 Total: 20+ Stories, 50–65 Points

EPIC 18: UX/DESIGN SYSTEM

SRS Traceability: NFR8, NFR17–NFR18
Priority: HIGH (Sprint 1–4, parallel)
Total Stories: 15
Estimated Story Points: 35–45

EPIC OBJECTIVE

Establish consistent design language, accessibility compliance, dark mode support, and i18n framework across web/iOS/Android.

Features:

- Design system components (typography, colors, buttons, cards, modals)

- WCAG 2.1 AA compliance audit

- Dark mode implementation

- Internationalization (i18n) framework setup

- Brand guidelines documentation

Epic 18 Total: 15 Stories, 35–45 Points

EPIC 19: NON-FUNCTIONAL REQUIREMENTS & QA

SRS Traceability: NFR1–NFR20
Priority: HIGH (Sprint 6–8)
Total Stories: 25+
Estimated Story Points: 60–80

EPIC OBJECTIVE

Ensure system meets all performance, security, accessibility, and quality targets through comprehensive testing and monitoring.

Target Metrics:

- API latency p95: < 500ms

- ML inference: < 4 seconds

- App launch time: < 2 seconds

- WCAG 2.1 AA compliance: 100%

- ML fairness: ±5% accuracy across Fitzpatrick I–VI

- System uptime: ≥ 99%

- Security vulnerabilities: 0 critical

Epic 19 Total: 25+ Stories, 60–80 Points

SPRINT PLANNING ROADMAP

16-WEEK MVP DEVELOPMENT PLAN

| Sprint | Duration | Theme | Velocity | Focus EPICs | Key Deliverables |
| --- | --- | --- | --- | --- | --- |
| 1 | Wk 1–2 | Foundation | 50 | 1, 16, 17 | Auth, DB schema, ML pipeline setup |
| 2 | Wk 3–4 | Scanning | 44 | 2, 16, 18 | Guided scan UI, ML models, fairness baseline |
| 3 | Wk 5–6 | Intelligence | 41 | 3, 5, 16 | Digital Twin, ingredient database, safety scoring |
| 4 | Wk 7–8 | Routines | 32 | 6, 5 | Routine builder, My Shelf inventory |
| 5 | Wk 9–10 | Analytics | 37 | 7, 8, 9 | Progress charts, env integration, forecasting |
| 6 | Wk 11–12 | Polish | 45 | 12, 13, 18, 19 | Risk Radar, experiments, accessibility audit |
| 7 | Wk 13–14 | Apps | 50 | 16, 17 | Web/iOS/Android optimization, final ML tuning |
| 8 | Wk 15–16 | Launch | 55+ | 19 | QA, performance tuning, launch readiness |

Table 1: MVP Sprint Planning: 16-week timeline across 8 two-week sprints

SPRINT-BY-SPRINT BREAKDOWN

SPRINT 1 (Weeks 1–2): FOUNDATION

Velocity Target: 50 story points
Focus: Authentication, database schema, ML pipeline, infrastructure

| Story ID | Story Name | Points | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| 1.1.1 | Email Registration | 8 | Backend #1 | None |
| 1.1.2 | Email Login & Session Mgmt | 8 | Backend #2 | 1.1.1 |
| 1.6 | Profile Management & Settings | 5 | Frontend | 1.1.2 |
| 1.9 | Privacy Policy & Consent UI | 5 | Frontend | 1.1.2 |
| 16.1 | ML Pipeline Setup (DVC, MLflow) | 8 | ML Lead | None |
| 16.2 | Dataset Import & Annotation | 5 | Data Scientist | 16.1 |
| 17.1 | CI/CD Pipeline (GitHub Actions) | 8 | DevOps | None |
| 17.2 | Database Setup (PostgreSQL, migrations) | 5 | Backend Lead | 17.1 |
| 17.3 | Monitoring & Logging Setup (ELK) | 5 | DevOps | 17.1 |
| 18.1 | Design System Foundation | 5 | Design Lead | None |

Sprint Goals:

- ✓ Users can register and login securely

- ✓ Database and infrastructure ready for development

- ✓ ML pipeline running (models ready for import)

- ✓ CI/CD pipeline deploying to dev environment

Definition of Done (All Stories):

- ☐ All acceptance criteria verified

- ☐ ≥ 90% unit test coverage

- ☐ Code reviewed by 2+ engineers

- ☐ Deployed to dev environment

- ☐ Documented in wiki/runbooks

SPRINT 2 (Weeks 3–4): SCANNING

Velocity Target: 44 story points
Focus: Guided scan UI, face detection, concern scoring

| Story ID | Story Name | Points | Owner |
| --- | --- | --- | --- |
| 2.1.1 | Guided Scan UI with Real-Time Feedback | 13 | Frontend Lead + Mobile |
| 2.2 | AI Skin Concern Detection Engine | 13 | ML Lead + Backend |
| 2.3 | Skin Type Classification | 8 | ML Lead |
| 2.4 | Confidence Scoring & Uncertainty | 5 | ML Lead |
| 2.7 | Scan Result Display & Breakdown | 8 | Frontend |
| 18.2 | Component Library (buttons, cards, modals) | 5 | Design Lead |

Sprint Goals:

- ✓ Users can perform guided face scans on web, iOS, Android

- ✓ AI models detecting acne, redness, pigmentation, texture with confidence scores

- ✓ Scan results displayed in user-friendly format

- ✓ Fairness baseline established (model accuracy on Fitzpatrick I–VI)

SPRINT 3 (Weeks 5–6): INTELLIGENCE

Velocity Target: 41 story points
Focus: Digital Twin, ingredient database, product safety

| Story ID | Story Name | Points | Owner |
| --- | --- | --- | --- |
| 3.1 | Digital Twin Model & State Vector | 13 | Backend + ML |
| 3.2 | Regional Analysis (Forehead, Cheeks, etc.) | 8 | Backend + ML |
| 5.1 | Ingredient Database & OCR Pipeline | 10 | Backend |
| 5.2 | Product Safety Classification | 8 | Backend |
| 3.3 | Timeline Visualization | 5 | Frontend |
| 18.3 | Dark Mode Support | 5 | Frontend |

Sprint Goals:

- ✓ Digital Twin built and stored for each user

- ✓ Ingredient database loaded and searchable

- ✓ Product scan (barcode/OCR) → safety classification working

SPRINT 4 (Weeks 7–8): ROUTINES

Velocity Target: 32 story points
Focus: Routine builder, My Shelf inventory, product interactions

| Story ID | Story Name | Points | Owner |
| --- | --- | --- | --- |
| 6.1 | Routine Builder Engine (AM/PM) | 13 | Backend |
| 6.2 | My Shelf Inventory Management | 8 | Backend + Frontend |
| 6.3 | Product Interaction Checker | 8 | Backend |
| 6.4 | Routine Safety Score | 5 | ML Lead |

Sprint Goals:

- ✓ Users can build personalized AM/PM routines using My Shelf

- ✓ Product interactions detected and warned

- ✓ Routine Safety Score calculated and displayed

SPRINT 5 (Weeks 9–10): ANALYTICS & ENVIRONMENT

Velocity Target: 37 story points
Focus: Progress tracking, environment integration, forecasting

| Story ID | Story Name | Points | Owner |
| --- | --- | --- | --- |
| 7.1 | Progress Charts (7/30/90-day) | 8 | Frontend + Backend |
| 7.2 | Before/After Comparison | 5 | Frontend |
| 8.1 | Environmental Intelligence Integration | 10 | Backend |
| 8.2 | Skin Weather Score | 5 | Backend + ML |
| 9.1 | Predictive Forecasting Model | 13 | ML Lead |

Sprint Goals:

- ✓ Users see progress charts and historical trends

- ✓ Environmental data (UV, humidity, pollution) integrated

- ✓ 7/30/90-day predictions working

SPRINT 6 (Weeks 11–12): POLISH & ADVANCED

Velocity Target: 45 story points
Focus: Risk Radar, experiments, accessibility, QA

| Story ID | Story Name | Points | Owner |
| --- | --- | --- | --- |
| 12.1 | Dermatology Risk Radar | 10 | Backend + ML |
| 13.1 | N-of-1 Experiments Engine | 13 | Backend + Frontend |
| 2.5 | Fairness Monitoring Dashboard | 8 | ML Lead |
| 19.1 | WCAG 2.1 AA Accessibility Audit | 8 | QA Lead |
| 18.4 | i18n Framework Setup | 5 | Frontend |
| 19.2 | Security Penetration Testing | 5 | DevOps/Security |

Sprint Goals:

- ✓ Dermatology Risk Radar live and monitoring multi-scan trends

- ✓ Users can start N-of-1 experiments

- ✓ Accessibility audit completed, major issues fixed

- ✓ Security testing completed

SPRINT 7 (Weeks 13–14): APPS & OPTIMIZATION

Velocity Target: 50 story points
Focus: Cross-platform optimization, final model tuning

| Story ID | Story Name | Points | Owner |
| --- | --- | --- | --- |
| 17.4 | Web App Optimization (Lighthouse) | 8 | Frontend |
| 17.5 | iOS App Performance Tuning | 10 | Mobile |
| 17.6 | Android App Performance Tuning | 10 | Mobile |
| 16.3 | ML Model Optimization (quantization) | 13 | ML Lead |
| 19.3 | Load Testing & Capacity Planning | 8 | DevOps |
| 1.10 | Multi-Language Onboarding (Spanish/French/German) | 5 | Frontend |

Sprint Goals:

- ✓ All apps (web, iOS, Android) performing optimally

- ✓ ML models optimized for edge deployment

- ✓ System capacity validated for 100K+ concurrent users

SPRINT 8 (Weeks 15–16): LAUNCH

Velocity Target: 55+ story points
Focus: Final QA, bug fixes, launch readiness

| Story ID | Story Name | Points | Owner |
| --- | --- | --- | --- |
| 19.4 | Final QA & Regression Testing | 15 | QA Lead |
| 19.5 | Launch Checklist & Runbooks | 8 | PM + DevOps |
| 19.6 | Performance Monitoring Setup | 8 | DevOps |
| 19.7 | User Support Documentation | 5 | PM + QA |
| 19.8 | App Store Submission (iOS/Android) | 5 | Mobile + PM |
| 16.4 | Model Monitoring & Rollback Procedures | 8 | ML Lead |
| 17.7 | Launch Day Incident Response Plan | 5 | DevOps + PM |

Sprint Goals:

- ✓ Zero critical bugs

- ✓ All platforms pass final QA

- ✓ Documentation complete

- ✓ Ready for production launch

MVP SUCCESS CRITERIA

Upon completion of Sprint 8, the MVP must satisfy:

| Category | Target | Owner | Verification |
| --- | --- | --- | --- |
| Feature | All 60 MVP stories shipped | Product Team | Sprint board = 100% complete |
| Performance | API latency p95 < 500ms | Backend Lead | APM monitoring dashboard |
| Performance | App launch < 2 sec | Frontend Lead | Lighthouse, WebPageTest |
| Fairness | ML ±5% accuracy (Fitzpatrick I–VI) | ML Lead | Validation dataset audit |
| Accessibility | WCAG 2.1 AA 100% | QA Lead | Third-party audit report |
| Reliability | Severity 1–2 bugs < 1% | QA Lead | Production error tracking |
| Retention | Day 30 > 40% | Product Lead | Analytics cohort analysis |
| Satisfaction | App store ≥ 4.5 stars | Product Lead | App store reviews |

Table 2: MVP Launch Success Criteria

RISK REGISTER & MITIGATION

| Risk ID | Risk Description | Impact | Probability | Mitigation Strategy | Owner | Contingency | Monitor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | ML bias across skin tones (model accuracy variance > 5% between Fitzpatrick I–VI) | Critical | Medium | Fairness testing from Sprint 1 Day 1; diverse training datasets; stratified validation; automated fairness dashboards; monthly bias audits | ML Lead | Expand dataset; retrain with bias correction techniques | Fairness audit reports, accuracy by skin tone |
| R2 | User adoption / retention (Day 30 retention < 40%) | High | High | Invest heavily in gamification (badges, streaks, burnout prevention); micro-lessons embedded in every feature; A/B test onboarding flows; push notification strategy | Product Lead | Pivot to simpler core features; launch referral incentives | Cohort retention dashboards, NPS scores |
| R3 | API scalability bottlenecks (latency p95 > 500ms under load) | High | Medium | Load testing starting Sprint 1; auto-scaling policies on Kubernetes; CDN for static assets; database query optimization; caching layers (Redis) | Backend Lead | Increase infrastructure budget; consider serverless migration | APM dashboards, load test results |
| R4 | Data privacy breach / unauthorized access | Critical | Low | AES-256 encryption at rest + TLS 1.3 in transit; regular security audits (quarterly); incident response plan drafted; employee access controls; GDPR compliance review | Security Lead | Immediate breach response; customer notification; regulatory filings | Security audit reports, access logs |
| R5 | Cross-platform feature parity missing (iOS 2 weeks behind Android) | Medium | Medium | Dedicated platform-specific stories in sprints; phased feature rollout strategy; cross-platform testing early in cycle; shared architecture patterns | Tech Lead | Hire additional mobile engineer; consider cross-platform framework | Platform launch dates, feature parity checklist |
| R6 | Model accuracy regression (latency increases or accuracy drops after model update) | High | Medium | Continuous model monitoring with drift detection; A/B testing on new models before production deployment; automated rollback procedures if performance drops > 2% | ML Lead | Revert to previous model version; emergency retrain | Model performance dashboards, A/B test results |
| R7 | OCR/barcode failures (ingredient extraction fails > 15% of scans) | Medium | Medium | Fallback to manual ingredient entry (user pastes ingredient list); crowd-sourced ingredient database validation; user feedback loop to improve models; weekly OCR accuracy audits | Backend Lead | Hire QA team to manually verify top 1000 products | OCR accuracy metrics, manual entry fallback usage |
| R8 | Third-party API failures (weather, maps services down; no graceful degradation) | Medium | Low | Implement graceful degradation: cached fallback data (24-hour TTL); clear UI labels (\"Forecast based on cached data\"); alert users to unavailability; multi-provider strategy (backup weather API) | DevOps Lead | Use historical average data; disable feature temporarily | API uptime monitoring, fallback activation logs |
| R9 | Team knowledge loss / key person risk (ML Lead departing mid-project) | High | Low | Comprehensive documentation; pair programming sessions; weekly knowledge-sharing meetings; cross-training on critical systems; documented runbooks for model training, deployment | PM Lead | Hire freelance ML consultant; reduce scope; delay Phase 2 | Team turnover tracking, documentation completeness |
| R10 | Regulatory compliance gaps (EU medical device classification or GDPR violations discovered late) | Critical | Medium | Legal review of all customer-facing claims (no diagnosis language); GDPR Data Protection Impact Assessment (DPIA) completed pre-launch; compliance team integrated in Sprint 1 | Product Lead + Legal | Pivot messaging; delay launch; invest in compliance fixes | Compliance checklist, legal review approvals |

Risk Review Cadence: Weekly during daily standups; formal risk review at end of each sprint (Sprint Planning + Retrospective)

RESOURCE ALLOCATION

RECOMMENDED TEAM STRUCTURE: 12–14 ENGINEERS (16-WEEK MVP)

BACKEND TEAM (4–5 engineers)

- 1 Tech Lead (API architecture, database schema design, security strategy, code reviews, architectural decisions)

  - Hours: 40/week, Sprint 1–8

  - Owns: Endpoints for auth, routines, product intelligence; database migrations; performance optimization

- 2 Backend Engineers (authentication flows, routine builder, product intelligence)

  - Hours: 40/week each, Sprint 1–8

  - Story allocation: Auth (Sprint 1–2), Product Intelligence (Sprint 3–4), Routine Builder (Sprint 4–5)

- 1 Senior Backend Engineer (infrastructure, ML model serving, security hardening)

  - Hours: 40/week, Sprint 1–8

  - Owns: DevOps pipeline, database scaling, model inference API, security audits

- 1 Optional Junior Backend Engineer (bug fixes, documentation, QA support)

  - Hours: 40/week, Sprint 4–8 (added mid-project based on velocity)

FRONTEND TEAM (3–4 engineers)

- 1 Tech Lead / Architect (design system, web app architecture, accessibility, cross-platform consistency)

  - Hours: 40/week, Sprint 1–8

  - Owns: Component library, design tokens, responsive web, WCAG compliance

- 2 Web Engineers (React/TypeScript implementation for web platform)

  - Hours: 40/week each, Sprint 1–8

  - Story allocation: UI/UX (Sprint 1–2), Routines Dashboard (Sprint 4–5), Analytics (Sprint 5–6)

- 1 Mobile Engineer (iOS native + Android native or React Native)

  - Hours: 40/week, Sprint 1–8

  - Story allocation: Guided scan UI (Sprint 2), mobile optimizations (Sprint 7), app store submission (Sprint 8)

ML TEAM (2–3 engineers)

- 1 ML Engineer (model architecture, training pipelines, optimization)

  - Hours: 40/week, Sprint 1–8 (parallel track)

  - Story allocation: Pipeline setup (Sprint 1), model training (Sprint 2–3), fairness (Sprint 3), edge optimization (Sprint 7)

- 1 Data Scientist (datasets, data annotation, model evaluation)

  - Hours: 40/week, Sprint 1–8 (parallel track)

  - Story allocation: Dataset curation (Sprint 1), fairness testing (Sprint 2–3), model monitoring (Sprint 6–8)

- 1 Optional Second Data Scientist (fairness audits, explainability, A/B testing)

  - Hours: 40/week, Sprint 2–8 (added if budget allows)

PRODUCT & QA (2–3 engineers)

- 1 Product Manager (backlog prioritization, stakeholder communication, roadmap planning)

  - Hours: 40/week, Sprint 1–8

  - Owns: Sprint planning, feature prioritization, stakeholder demos, post-launch roadmap

- 1 QA Engineer (test automation, regression testing, accessibility audit)

  - Hours: 40/week, Sprint 1–8

  - Story allocation: Test harness setup (Sprint 1), automation (Sprint 2–6), accessibility audit (Sprint 6), final QA (Sprint 8)

- 1 DevOps Engineer (CI/CD, infrastructure, monitoring, deployment)

  - Hours: 40/week, Sprint 1–8

  - Story allocation: CI/CD pipeline (Sprint 1), environment setup (Sprint 1–2), monitoring (Sprint 6–8), launch readiness (Sprint 8)

OPTIONAL ROLES (Consider if budget allows)

- Security Engineer (0.5 FTE): Penetration testing, security audits, compliance (GDPR, medical device readiness)

- UX Researcher (0.5 FTE): User testing, usability studies, accessibility research

- Technical Writer (0.5 FTE): API documentation, runbooks, user guides

COST ESTIMATION (16-Week MVP Development)

LABOR COSTS (Core Team: 12–14 FTE)

| Role | Headcount | Avg Salary/Month | Fully Loaded Cost* | Subtotal (16 weeks / 3.7 months) |
| --- | --- | --- | --- | --- |
| Tech Leads (Backend, Frontend, Product) | 3 | $16,000 | $19,200 | $212,160 |
| Senior Engineers (Backend, DevOps, ML) | 2 | $14,000 | $16,800 | $123,360 |
| Backend Engineers | 2 | $11,000 | $13,200 | $97,440 |
| Frontend/Web Engineers | 2 | $10,500 | $12,600 | $92,640 |
| Mobile Engineer | 1 | $11,500 | $13,800 | $50,760 |
| ML Engineer | 1 | $13,000 | $15,600 | $57,420 |
| Data Scientists | 2 | $12,000 | $14,400 | $105,840 |
| QA Engineer | 1 | $9,500 | $11,400 | $42,120 |
| DevOps Engineer | 1 | $12,000 | $14,400 | $53,040 |
| Subtotal (12 FTE Core) | 12 | — | — | $834,780 |
| Optional: Junior Backend (Sprints 4–8) | 1 | $8,500 | $10,200 | $35,700 |
| Optional: Security Engineer (0.5 FTE) | 0.5 | $14,000 | $16,800 | $31,080 |
| Optional: UX Researcher (0.5 FTE) | 0.5 | $11,000 | $13,200 | $24,420 |
| Optional: Technical Writer (0.5 FTE) | 0.5 | $9,000 | $10,800 | $19,980 |
| Subtotal (Optional: 2.5 FTE) | 2.5 | — | — | $111,180 |
| TOTAL LABOR (12–14.5 FTE) | 12–14.5 | — | — | $834,780–$945,960 |

*Fully loaded cost includes: salary + 20% benefits + equipment + workspace rental allocation

INFRASTRUCTURE & THIRD-PARTY SERVICES

| Category | Monthly Cost | Notes | Subtotal (16 weeks) |
| --- | --- | --- | --- |
| Cloud Infrastructure | — | — | — |
| AWS/GCP/Azure compute (app servers, databases, ML inference) | $4,500 | Auto-scaling, redundancy, multi-region | $16,650 |
| Cloud storage (S3/GCS for images, backups) | $1,200 | Encrypted, versioned, 90-day retention | $4,440 |
| CDN (CloudFront/Cloudflare) | $800 | Static assets, image optimization | $2,960 |
| Databases & Caching | — | — | — |
| PostgreSQL (managed, RDS/Cloud SQL) | $1,500 | Multi-AZ, automated backups, replication | $5,550 |
| Redis cache (managed) | $400 | Session cache, rate limiting, real-time data | $1,480 |
| Monitoring & Observability | — | — | — |
| APM Platform (Datadog/New Relic) | $1,200 | Performance tracking, error monitoring, alerts | $4,440 |
| Log aggregation (ELK / LogRocket) | $600 | Centralized logging, search, retention | $2,220 |
| Error tracking (Sentry) | $300 | JavaScript/Python error capture | $1,110 |
| External APIs & Services | — | — | — |
| Email service (SendGrid/AWS SES) | $500 | Transactional emails, verification, newsletters | $1,850 |
| Weather API (OpenWeatherMap / WeatherAPI) | $200 | Real-time UV, pollution, climate data | $740 |
| Maps API (Google Maps / Mapbox) | $300 | Geolocation, provider directory | $1,110 |
| Product database (Open Beauty Facts API, INCIDecoder) | $400 | Ingredient reference data | $1,480 |
| SMS service (optional, Twilio) | $200 | 2FA, notifications (if implemented) | $740 |
| ML & Data Tools | — | — | — |
| MLflow/Kubeflow (model tracking) | $300 | Pipeline orchestration, experiment tracking | $1,110 |
| Data labeling platform (Label Studio / Prodigy license) | $400 | Annotation tool for training data | $1,480 |
| GPU compute for model training (SageMaker / Vertex AI) | $2,000 | Cloud-based ML training, not local | $7,400 |
| Development & Collaboration | — | — | — |
| GitHub Enterprise (CI/CD, code hosting) | $250 | Private repos, Actions, security scanning | $925 |
| JIRA / Azure DevOps (project management) | $150 | Sprint planning, issue tracking | $555 |
| Slack (team communication) | $100 | Chat, integrations (assuming Pro tier) | $370 |
| Design tools (Figma team license) | $200 | UI/UX design, prototyping | $740 |
| Testing & QA | — | — | — |
| Load testing platform (K6 Cloud) | $200 | Performance testing, spike tests | $740 |
| Test automation (BrowserStack / Sauce Labs) | $400 | Cross-browser/device testing | $1,480 |
| Security scanning (Snyk + OWASP scanning) | $300 | Dependency scanning, vulnerability detection | $1,110 |
| TOTAL Infrastructure & Third-Party | $15,600/month | — | $57,720 |

PROJECT CONTINGENCY & MISCELLANEOUS

| Item | Cost | Notes |
| --- | --- | --- |
| Contractor support (domain experts, fairness audit) | $25,000 | Specialized consulting as needed |
| Hardware & equipment (laptops, mobile devices for testing) | $10,000 | Development machines, test devices |
| Training & certifications (AWS, ML, accessibility) | $5,000 | Team upskilling |
| Legal & compliance (GDPR, medical device readiness review) | $15,000 | Early-stage regulatory assessment |
| Contingency buffer (10% of total) | $98,000 | Unforeseen costs, overruns |
| Subtotal Contingency & Misc | $153,000 | — |

TOTAL MVP DEVELOPMENT COST

| Budget Line | Cost Range | Notes |
| --- | --- | --- |
| Labor (12–14.5 FTE) | $834,780–$945,960 | Salary + benefits fully loaded |
| Infrastructure & Services | $57,720 | Cloud, APIs, tools, monitoring |
| Contingency & Misc | $153,000 | ~10% buffer for unknowns |
| GRAND TOTAL | $1,045,500–$1,156,680 | Approximately $1.05M–$1.16M |

Cost Breakdown by Category:

- Labor: 78–82% (bulk of investment in engineering talent)

- Infrastructure: 5% (cloud costs, relatively predictable)

- Contingency: 10–15% (buffer for scope creep, unexpected issues)

Cost Optimization Opportunities:

- Use open-source tools (MLflow, Kubernetes) to reduce licensing costs

- Leverage free/low-cost datasets (Open Beauty Facts, public dermatology datasets) for initial MVP

- Negotiate volume discounts with cloud provider (AWS, GCP)

- Consider hiring offshore/nearshore engineers for non-critical roles (QA, documentation)

PHASE 2 RELEASE PLAN (12 WEEKS POST-MVP)

After MVP launch (16 weeks), Phase 2 advanced features will be released in subsequent sprints:

| Epic | Stories | Points | Priority | Timeline |
| --- | --- | --- | --- | --- |
| Advanced Forecasting | 3 | 24 | High | Weeks 1–4 |
| Full Environmental Intel | 3 | 21 | High | Weeks 2–6 |
| Counterfeit Detection | 2 | 13 | Medium | Weeks 5–8 |
| Dermatology Risk Radar Adv | 2 | 16 | High | Weeks 6–10 |
| External APIs | 2 | 15 | Medium | Weeks 8–12 |
| N-of-1 Analytics | 2 | 12 | Medium | Weeks 10–12 |
| PHASE 2 TOTAL | 13 | 101 | — | 12 weeks |

Table 3: Phase 2 Release Plan: Advanced features post-launch

TESTING STRATEGY

TEST PYRAMID

- Unit Tests: 50% (framework-specific, model inference, business logic)

- Integration Tests: 30% (API endpoints, database transactions, external service mocks)

- E2E Tests: 15% (full user flows: register → scan → routine → track)

- Performance Tests: 5% (load testing, stress testing, spike testing)

CONTINUOUS INTEGRATION / CONTINUOUS DEPLOYMENT (CI/CD)

GitHub Actions Pipeline:

- On Pull Request:

  - Lint (ESLint, Pylint)

  - Unit tests (Jest, pytest)

  - Security scan (OWASP, SonarQube)

  - Build artifact

- On Merge to main:

  - Deploy to staging environment

  - Smoke tests

  - Performance baseline comparison

  - Manual QA signoff

- On Release Tag:

  - Deploy to production

  - Canary rollout (10% traffic, 24 hours)

  - Full rollout if no errors detected

ACCESSIBILITY TESTING

- Manual: Keyboard navigation, screen reader testing (NVDA, JAWS, VoiceOver)

- Automated: axe DevTools, WAVE, Lighthouse

- Audit: Third-party accessibility consultant (quarterly)

SECURITY TESTING

- Quarterly: Penetration testing by external firm

- Continuous: Dependency scanning (Snyk, Dependabot)

- Monthly: OWASP Top 10 vulnerability scan

APPENDIX: GLOSSARY

| Term | Definition |
| --- | --- |
| Digital Twin™ | Longitudinal, multi-dimensional representation of user's skin state |
| Skin Mood Index™ | Qualitative label of current skin state (balanced, inflamed, etc.) |
| My Shelf | User's inventory of scanned/added skincare products |
| Routine Safety Score | Composite metric (0–100) estimating irritation/risk of routine |
| Microbiome Disruption Index | Quantitative indicator of skin microbiome disturbance risk |
| Dermatology Risk Radar | Trend-based monitoring engine analyzing multi-scan trajectories |
| Skin Weather Score | Daily rating (0–100) of how friendly climate is to user's skin |
| N-of-1 Experiment | User-run, AI-tracked personal skincare experiment (baseline → intervention → analysis) |
| Fitzpatrick Scale | Skin tone classification system (I–VI, light to dark) |

DOCUMENT CONTROL

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 5.0 | Nov 30, 2025 | Product Team | Comprehensive product backlog V5 with full sprint breakdown |
| 4.0 | Nov 30, 2025 | Product Team | Ultra-detailed DOCX format |
| 3.0 | Nov 30, 2025 | Product Team | Clean agile-ready format |
| 1.0–2.0 | Nov 30, 2025 | Product Team | Initial drafts |

APPROVAL SIGNATURES

Product Manager: ___________________________________ Date: __________

Tech Lead: ___________________________________ Date: __________

ML Lead: ___________________________________ Date: __________

QA Lead: ___________________________________ Date: __________

Document Owner: Product Manager
Next Review: End of Sprint 2 (Week 6)
Distribution: Development Team, Leadership, Stakeholders, Investors

FINAL BACKLOG CHECKLIST

Before proceeding to Sprint 1, verify:

- ☐ All 19 EPICs mapped to SRS requirements (FR1–FR60, UR1–UR22, BR1–BR15, NFR1–NFR20)

- ☐ 60 MVP stories identified and estimated (total ~350–400 story points)

- ☐ All stories have acceptance criteria (≥ 10 per story minimum)

- ☐ Dependencies between stories mapped (blockers identified)

- ☐ Risks identified and mitigation strategies assigned (10 major risks tracked)

- ☐ Resource team finalized (12–14 engineers assigned to roles)

- ☐ Budget approved ($1.05M–$1.16M for 16-week MVP)

- ☐ Infrastructure baseline established (CI/CD, databases, monitoring)

- ☐ Stakeholder alignment confirmed (leadership signoff on roadmap)

- ☐ Sprint 1 backlog ready for Day 1 kickoff

- ☐ Definition of Done template approved by team

- ☐ Success metrics baseline established (current state documented)

NEXT STEPS POST-BACKLOG APPROVAL

Week of December 1–2, 2025:

- Conduct Sprint 0 kickoff (team formation, tool setup, sprint board creation)

- Finalize infrastructure (dev/staging/prod environments provisioned)

- Establish baseline metrics for all success KPIs

- Conduct fairness baseline audit on ML models (prepare for Sprint 2)

- Create team wiki with architecture diagrams, API specifications, runbooks

Sprint 1 Kickoff (December 9, 2025):

- Begin work on Stories 1.1.1 (Email Registration) and 1.1.2 (Email Login)

- Parallel: Set up ML pipeline, deploy CI/CD, prepare design system

- Daily standups 10:00 AM GMT (15-minute time-boxed)

- End-of-sprint demo Thursday December 19, 2025 (4:00 PM GMT)

APPROVAL & SIGN-OFF

This Product Backlog V5 represents the complete scope, timeline, resource allocation, and success criteria for the AI Skincare Intelligence System MVP (Release 1.0) and Phase 2 roadmap.

Required Approvals:

| Stakeholder | Role | Approval Date | Signature |
| --- | --- | --- | --- |
| Product Manager | Product Strategy & Vision | — | __________________ |
| Tech Lead | Engineering & Architecture | — | __________________ |
| ML Lead | ML/AI & Fairness Strategy | — | __________________ |
| QA Lead | Quality & Testing | — | __________________ |
| VP Engineering | Resource Allocation & Budget | — | __________________ |
| CFO (or Finance) | Budget Approval ($1.05M–$1.16M) | — | __________________ |
| Legal / Compliance | Regulatory Readiness (GDPR, medical device) | — | __________________ |

REVISION HISTORY

| Version | Date | Author | Changes | Status |
| --- | --- | --- | --- | --- |
| 5.0 | Nov 30, 2025 | Product Team | FINAL: Ultra-detailed product backlog V5 with full sprint breakdown, detailed user stories (1.1.1 & 1.1.2 fully expanded), risk mitigation strategies, resource allocation with cost estimation, approval workflows | Ready for Sprint 1 |
| 4.0 | Nov 30, 2025 | Product Team | Comprehensive product backlog with epic summaries | Draft |
| 3.0 | Nov 30, 2025 | Product Team | Clean agile-ready format | Draft |
| 2.0 | Nov 30, 2025 | Product Team | Initial structured backlog | Draft |
| 1.0 | Nov 30, 2025 | Product Team | SRS-to-backlog mapping foundation | Internal |

Document Classification: Internal – Business Sensitive
Distribution: Development Team, Leadership, Stakeholders, Investors
Retention: Permanent (archived after project completion)
Review Cycle: Weekly team reviews; formal backlog refinement every sprint
Next Major Review: End of Sprint 2 (Week 6, December 19, 2025)

END OF AI SKINCARE INTELLIGENCE SYSTEM – PRODUCT BACKLOG V5.0
COMPREHENSIVE, AGILE-DRIVEN PRODUCT BACKLOG FOR MVP & PHASE 2 DELIVERY
Ready for Sprint 1 Kickoff: December 9, 2025
November 30, 2025